## Credit Tracker
TRUE Operations & Diversion - Credit Tracking Tool
UC Berkeley - The Gateway
# | Credit ID | Credit Name | Task | Frequency | Phase | Status | Priority | Evidence / Documents Needed | Owner | Notes / Progress
LEADERSHIP
1 | Lead 1 | Adopt zero waste goal (Upper Management) | Ensure the adopted zero waste goal from construction carries forward into operations. Review and update the goal/timeline annually. Post the goal visibly in building common areas. | Once + Annual Review | Before Opening | In Progress | Critical | Written zero waste goal document signed by upper management; timeline/plan document; photos of posted goals | Building Manager | "Divert 90% of waste from landfill" We can make signage but need it to be signed.
2 | Lead 2 | Review monthly diversion activities | Conduct monthly meeting to review waste diversion data (weights by stream), financial performance (hauling costs, savings), and identify corrective actions. Document minutes. | Monthly | Ongoing (Monthly) | In Progress | Critical | Monthly meeting minutes/agendas; waste reports reviewed; attendee lists; copies of reports generated for leadership | Building Manager | Can incorporate into our meetings.
3 | Lead 3 | Incentivize employee participation | Set up a suggestion system for zero waste ideas (physical or digital). Recognize/reward employees making outstanding zero waste contributions (awards, shoutouts, incentives). | Monthly / Quarterly | At Opening | In Progress | Medium | Documentation of suggestion system; records of awards/recognition given; photos of announcements | Building Manager | p 5 on manual
4 | Lead 4 | Take responsibility for products/packaging | Usually N/A for academic buildings unless the facility produces/distributes products. If applicable, set up take-back or EPR program. | N/A | N/A | Not Started | Low | N/A for academic building | N/A
5 | Lead 5 | Require vendor take-back responsibility | Negotiate vendor contracts/POs requiring at least one vendor to take back packaging or reimburse. Continue curtain wall reusable crate model for future vendors. | At Contract Signing + Quarterly Review | Before Opening | Not Started | High | Vendor contracts with take-back clauses; RFPs/bid specs; invoices showing credits; photos of reusable packaging | Purchasing
6 | Lead 6 | Promote zero waste in community | Host, sponsor, or participate in at least one community event promoting zero waste annually. Continue GreenBuild-style presentations. | Annually / Biannually | Ongoing (Annually) | Not Started | Medium | Event photos; flyers/promotional materials; official letters; press releases; presentation slides | Cal Zero Waste
TRAINING
7 | Train 1 | Provide zero waste goal/policy to all employees | Distribute the zero waste policy to all building occupants via orientation packet, department handbook, and/or email. Ensure policy is posted in common areas near bins. | Onboarding + Annually | Before Opening | In Progress | Critical | Copy of policy in handbook/website; photos of posted policy; email distribution records | Building Manager
8 | Train 2 | Incorporate zero waste into orientation | Add zero waste sorting rules, bin locations, and contamination examples to mandatory orientation for ALL building occupants (faculty, staff, students, vendors). | Every New Hire / Onboarding | Before Opening | In Progress | Critical | Orientation slides/handouts with ZW content; agendas showing ZW as topic; attendance logs | Building Manager
9 | Train 3 | Quarterly zero waste communications | Send zero waste updates at least quarterly: contamination alerts, diversion rate progress, tips, recognition. Use email, posters, digital screens, or meetings. | Quarterly (4x/year minimum) | Ongoing (Quarterly) | Not Started | Critical | 4 distinct quarterly communications (emails, posters, newsletter screenshots, etc.) with dates | Cal Zero Waste
10 | Train 4 | Label all collection receptacles + train sorting | Ensure ALL bins in the building are clearly labeled (recycling, compost, landfill) in multiple languages. Conduct regular site walks to verify. Train all occupants on what goes where. | Weekly Site Walks | Before Opening | Not Started | Critical | Photos of all labeled bins; training presentation/handouts; site walk logs | Building Manager
11 | Train 5 | Train purchasing agents | Train lab managers, PIs, department buyers on zero waste purchasing: prefer reusable over disposable, choose recyclable packaging, reference EPP catalog. | Annually | Before Opening | Not Started | High | Training slides/materials; attendance records; EPP purchasing guidelines distributed | Purchasing
12 | Train 6 | Include zero waste in evaluations/bonus | Work with HR to tie zero waste participation into employee evaluations or bonus structures for relevant staff. | Annually | At Opening | Not Started | Medium | Evaluation forms showing ZW criteria; bonus structure documentation | HR
13 | Train 7 | Dedicate a zero waste leader | Officially appoint at least one Zero Waste Champion or manager. Ensure their job description includes zero waste responsibilities and training others. | Once | Before Opening | In Progress | Critical | Job description with ZW responsibilities; appointment letter/email; org chart showing role | Building Manager
14 | Train 8 | Provide access to ongoing ZW training | Provide links to Cal Zero Waste training modules, sorting guides, and resources on building website or intranet. Ensure all occupants can access training at any time. | Quarterly / Annually | Before Opening | Not Started | High | Screenshot of training website/portal; link to online training resources; access logs if available | Cal Zero Waste
15 | Train 9 | TRUE Advisor on team | Maintain at least one TRUE Advisor credentialed person on the project team throughout operations. | Once + Maintain | Before Opening | Done | High | TRUE Advisor certificate(s); description of advisor role on the project | Andrea/UCB Team | Audrey, Reeya, and Sam are TRUE advisors
ZERO WASTE ANALYSIS
16 | ZWA 1 | Conduct physical waste audit | Conduct at least one physical waste audit during operations. Open bins, assess contamination, document material types and weights. Repeat at least quarterly. | Quarterly | Ongoing (Quarterly) | Not Started | Critical | Audit reports with weights/percentages; photographs of audit process; contamination logs | Building Manager
17 | ZWA 2 | Analyze audit results + implement recommendations | Analyze waste audit findings: identify contamination trends, material volumes, improvement opportunities. Write a report with recommendations. Implement changes and document results. | After Each Audit | Ongoing (Quarterly) | Not Started | Critical | Written audit analysis report; list of recommendations; documentation of changes implemented; before/after data | Building Manager
18 | ZWA 3 | Physical audit of recyclables | Conduct physical audit specifically of recycling stream: measure contamination percentage, identify types of contamination, track weight of recyclables vs. contaminants. | Quarterly | Ongoing (Quarterly) | Not Started | Critical | Recycling audit reports; contamination percentages; weight data for recyclables; photographs | Building Manager
19 | ZWA 4 | Add rejected recyclables to waste stream docs | Track contamination weight in recycling loads. Add rejected recyclables weight back into non-diversion (landfill) totals so diversion rate is honest. | Monthly (with diversion data) | Ongoing (Monthly) | Not Started | High | Diversion data showing contamination amounts added to non-diversion; hauler contamination reports | Building Manager
20 | ZWA 5 | Engage employees in waste audit/analysis | Involve building occupants in waste audits: recruit Zero Waste Champions for audit days, share results at all-hands or department meetings, incorporate feedback into action plans. | Quarterly | Ongoing (Quarterly) | Not Started | High | Photos of employee participation; feedback forms; meeting minutes showing results shared; action plans | Building Manager
UPSTREAM MANAGEMENT
21 | Upstream 1 | Work with vendors to eliminate non-recyclable packaging | Request vendors reduce or eliminate non-recyclable packaging. Document requests and outcomes. Continue reusable container programs from construction. | At Contract Signing + Quarterly | Before Opening | Not Started | High | Vendor communication (emails, letters); photos of previous vs. new packaging; vendor agreements | Purchasing
22 | Upstream 2 | Give preference to vendors with ZW goals | Ask vendors about their zero waste goals during procurement. Give preference to vendors actively pursuing zero waste when possible within public procurement rules. | At Procurement | At Opening | In Progress | Medium | Vendor questionnaires; documentation of preference criteria; vendor zero waste policies received | Purchasing
23 | Upstream 3 | Request vendors use 100% recyclable packaging | Request all vendors to use 100% recyclable packaging. Document the request and vendor responses. | At Contract Signing | Before Opening | In Progress | Medium | Written requests to vendors; vendor responses; packaging policy or agreement language | Purchasing
24 | Upstream 4 | Request vendors redesign products for reuse/recycling | Identify products that could be redesigned for reuse or recycling. Request at least one vendor to make changes. Document the process. | Annually | Ongoing (Annually) | Not Started | Low | Documentation of requests; vendor responses; photos of before/after product changes | Purchasing
ZERO WASTE REPORTING
25 | ZWR 1 | Document diversion by commodity or waste | Compile 12 months of ongoing diversion data and 12 months of baseline data for every commodity/waste stream. Break data down by month, calculate annual average diversion rate, and document any estimation methodology used. | Monthly tracking; annual compilation | Ongoing (Monthly) | Not Started | Critical | Data collection and tracking narrative, 12-month diversion tracking sheet by commodity/waste; baseline-year data; annual average diversion calculation; estimation methodology; at least one month of invoices, weight tickets, internal logs, or hauler reports verifying values | Multiple
26 | ZWR 2 | Track financial data for diversion and waste disposal | Track diversion and disposal financial data, including landfill disposal costs, avoided costs from diversion, recycling/compost hauling fees, and any recycling commodity revenue. Calculate annual cost/net program impact for baseline and reporting years. | Monthly tracking; annual compilation | Ongoing (Monthly) | Not Started | High | Financial tracking report for baseline and reporting year; monthly/annual cost and revenue summary; invoices, receipts, rebate statements, checks, or other proof for at least one month | Multiple
27 | ZWR 3 | Generate climate impact report using the U.S. EPA WARM Model | Enter annual material weights into the U.S. EPA WARM Model for all applicable waste/material types. Generate and save the climate impact report showing greenhouse gas and energy impacts of diversion efforts. | Annually | Ongoing (Annually) | Not Started | Medium | Report generated from the EPA’s WARM model | Cal Zero Waste
28 | ZWR 4 | Become an active participant of the U.S. EPA WasteWise program | Register Gateway/UC Berkeley as an active EPA WasteWise participant, submit current and baseline data during the reporting window, and maintain documentation of membership/participation. | Annually | Ongoing (Annually) | Not Started | Medium | WasteWise membership confirmation; official letter, email, or certificate of participation; annual data submission confirmation | Cal Zero Waste
RECYCLE
29 | Recycle 1 | Meet highest and best use for 80% of materials by weight | Identify applicable material categories generated at the facility and document highest and best use for each. Demonstrate that at least 80% of materials by weight meet highest and best use; if one material makes up 80% by weight, also document the next three largest streams. | Annually (update with diversion report) | Ongoing (Annually) | Not Started | High | Highest-and-best-use narrative for applicable material categories; calculations showing 80% by weight; supporting diversion data; documentation for next three largest streams if required | Cal Zero Waste | Will need to get the information from building managers or haulers
30 | Recycle 1.2 | Meet highest and best use for 100% of materials by weight | Identify highest and best use for all materials generated at the facility and demonstrate that 100% of materials by weight are following highest and best use. | Annually (update with diversion report) | Ongoing (Annually) | Not Started | Medium | Highest-and-best-use narrative for all material categories; calculations showing 100% by weight; supporting diversion data | Cal Zero Waste | Will need to get the information from building managers or haulers
31 | Recycle 2 | Determine end markets for recycled commodities | List every recycling service provider and obtain written documentation showing where recyclable commodities go for final processing after leaving the service provider site. | Annually + when vendors change | Ongoing (Annually) | Not Started | High | Narrative listing recycling service providers and locations; written end-market documentation from every recycling provider; vendor letters/emails; processing facility information | Cal Zero Waste | Will need to get the information from building managers or haulers
DIVERSION FROM LANDFILL, INCINERATION (WTE), AND ENVIRONMENT
32 | Diversion 1.1 | Diversion is 90.1-94.9% | Use 12 months of monthly tracking data to calculate whether annual average diversion is 90.1%–94.9%. Include all non-hazardous solid materials and identify any estimates/methodology used. | Monthly tracking (+ annual calculation) | Ongoing (Monthly) | Not Started | Critical | 12-month diversion tracking data by commodity/waste; annual average diversion calculation; verification for at least one month; estimation methodology if actual weights are unavailable | Cal Zero Waste | Will need raw data from haulers
33 | Diversion 1.2 | Diversion is 95%-96.9% | Use 12 months of monthly tracking data to calculate whether annual average diversion is 95%–96.9%. Include all non-hazardous solid materials and identify any estimates/methodology used. | Monthly tracking (+ annual calculation) | Ongoing (Monthly) | Not Started | High | 12-month diversion tracking data by commodity/waste; annual average diversion calculation; verification for at least one month; estimation methodology if actual weights are unavailable | Cal Zero Waste | Will need raw data from haulers
34 | Diversion 1.3 | Diversion is 97%-98.9% | Use 12 months of monthly tracking data to calculate whether annual average diversion is 97%–98.9%. Include all non-hazardous solid materials and identify any estimates/methodology used. | Monthly tracking (+ annual calculation) | Ongoing (Monthly) | Not Started | Medium | 12-month diversion tracking data by commodity/waste; annual average diversion calculation; verification for at least one month; estimation methodology if actual weights are unavailable | Cal Zero Waste | Will need raw data from haulers
35 | Diversion 1.4 | Diversion is 99-99.9% | Use 12 months of monthly tracking data to calculate whether annual average diversion is 99%–99.9%. Include all non-hazardous solid materials and identify any estimates/methodology used. | Monthly tracking (+ annual calculation) | Ongoing (Monthly) | Not Started | Low | 12-month diversion tracking data by commodity/waste; annual average diversion calculation; verification for at least one month; estimation methodology if actual weights are unavailable | Cal Zero Waste | Will need raw data from haulers
36 | Diversion 1.5 | Diversion is 100% | Use 12 months of monthly tracking data to calculate whether annual average diversion is 100%. Include all non-hazardous solid materials and identify any estimates/methodology used. | Monthly tracking (+ annual calculation) | Ongoing (Monthly) | Not Started | Low | 12-month diversion tracking data by commodity/waste; annual average diversion calculation; verification for at least one month; estimation methodology if actual weights are unavailable | Cal Zero Waste | Will need raw data from haulers
HAZARDOUS WASTE PREVENTION
37 | HWP 1 | Properly handle hazardous materials | Clearly label and safely store hazardous waste. Confirm waste labeling, storage, and disposal practices comply with HAZCOM, RCRA, and applicable federal, state, and local requirements. Train employees properly. | Once + Annual Review | Before and After | Not Started | Critical | Hazardous materials policy and training materials; storage, labeling, & training narrative; optional photos of storage/labeling system; any regulation compliance documentation | Building Manager
38 | HWP 2 | Save records for the duration of the project | Save all hazardous waste manifests and records for at least 3 years per state and local regulations. | Ongoing | Ongoing (Annually) | Not Started | High | Narrative documenting the maintenance of historical records including information of the organization responsible for record keeping (if applicable) | Building Manager
39 | HWP 3 | Reuse or recycle universal waste | Identify, collect and properly dispose of universal waste generated at the facility. Document collection, storage, and reuse/recycling/disposal process. | As generated + Annual Review | Ongoing (Annually) | Not Started | Critical | Narrative describing the universal wastes generated at the facility, and how they are collected and disposed | Building Manager
40 | HWP 4 | Reduce the use of hazardous chemicals/materials | Identify and implement a policy or standard practice to reduce or eliminate the use of hazardous chemicals/materials where feasible. | Once + Annual Review | Before and After | Not Started | Medium | Policy or standard practice reducing hazardous chemical/material use; narrative describing implementation | Building Manager
41 | HWP 5 | Collect universal wastes from employees and/or customers | Set up a process to collect universal wastes from employees and/or customers. Ensure proper disposal of collected universal wastes. | Ongoing / Scheduled Collection | Before and After | Not Started | Medium | Narrative describing the process, parameters, and frequency of collection. | Building Manager
REDUCE
42 | Reduce 1 | Identify at least 1 material the is being reduced/ track reduction | Documentation of the volume and/or weight of materials generated for a baseline period and for the present. | Baseline and Post-Reduction | Before and After | Not Started | Medium | Narrative describing material(s) reduced and calculation methodology; baseline weight/volume data; current weight/volume data; reduction calculations showing difference. | Cal Zero Waste
43 | Reduce 2 | Implement tracking programs to eliminate waste before it occurs. | Examine existing programs and develop a tool or tools to track the flow of materials throughout facility operations. Establish regular reviews of data to identify wasteful activities. | Monthly (with diversion data) | Ongoing (Monthly) | Not Started | High | Narrative describing tracking program/tool; screenshots, spreadsheets, reports, dashboards, or generated tracking reports showing material flow tracking. | Cal Zero Waste
44 | Reduce 3 | Adopt a goal to reduce size/ amt of product packaging. | Define reduction goals for inbound and outbound packaging. Create and implement a strategy to meet them. | Once | One-Time Setup | Not Started | High | Written packaging reduction goals; narrative describing strategy; baseline packaging data (inbound and outbound); implementation documentation. | Building Manager
45 | Reduce 4 | Go paperless for at least one major office function. | Implement the paperless program for at least one chosen office function and estimate the reduction in paper waste. | Once | One-Time Setup | Not Started | Medium | Narrative describing paperless office function; documentation showing implementation; estimate/calculation of paper waste reduction. | Building Manager
46 | Reduce 5 | Set all printers to Duplex print. | Ensure all printers within the facility are set to duplex printing. | Once | One-Time Setup | In Progress | Medium | Narrative describing duplex implementation; printer policy, IT settings documentation, screenshots, or vendor confirmation showing duplex defaults. | Building Manager
47 | Reduce 6 | Practice grasscycling for all mowed surfaces. | Include grasscycling as a requirement in the landscaping service contract’s scope of work. Alternatively, work with landlord to establish this practice or create a grasscycling policy and train employees on the practice. | At contract signing | One-Time Setup | Not Started | Medium | Landscaping contract language requiring grasscycling OR written grasscycling policy; employee/contractor training records; photos or documentation of implementation. | Building Manager
48 | Reduce 7 | Reduce yard trimming waste through native landscaping or Xeriscaping. | Install plants or use landscaping techniques that require little to no trimming and disposal of waste material. | Once | Before Opening | Not Started | Medium | Landscaping plan; plant lists/specifications; photos of native/xeriscape installations; narrative describing reduction in trimming waste. | Building Manager
REUSE
49 | Reuse 1 | Develop systems that emphasize reuse. | Identify single-use materials and establish a program to help reduce or eliminate at least one material/item type through the developed system. | When Single Use identified | As Needed | In Progress | High | Narrative describing reuse system; identification of targeted single-use item; documentation showing elimination/reduction program; before/after data if available. | Cal Zero Waste | pg 11 manual
50 | Reuse 2 | Document pallet and shipping container reuse. | Establish process to track and document the reuse of pallets, incoming shipping containers and outgoing shipping containers monthly, by weight. | Monthly | Ongoing (Monthly) | Not Started | High | Monthly pallet/shipping container tracking logs by weight; reuse records; spreadsheets; invoices or shipping documentation supporting quantities. | Multiple
51 | Reuse 3 | Implement reusable transport containers. | Utilize reusable plastic, metal, wood, or other durable material containers for transporting items or supplies. | Once | Before Opening | Not Started | High | Photos of reusable transport containers; purchase records; written procedures showing use of reusable containers. | Building Manager
52 | Reuse 4 | Establish program to reuse office supplies and materials. | ReUse station: a process to collect and redistribute unwanted office supplies and/or materials internally or externally. | Once | Before Opening | In Progress | Medium | ReUse Station procedures; photos; redistribution logs; narrative describing collection and reuse process. | Cal Zero Waste | pg. 8 manual
53 | Reuse 5 | Use reusable/ durable food serviceware. | Provide reusable/durable alternatives to disposable service ware in employee break rooms and common areas, outline waste reduction and savings. | Once | Before Opening | In Progress | Medium | Photos of reusable dishware and utensils; purchasing records; narrative describing implementation; estimate of disposable reduction and savings. | Cal Zero Waste | Reusables page
54 | Reuse 6 | Donate all food safe for human consumption. | Determine where food fit for human consumption could be preserved and donated. | As leftover food is generated | As Needed | Not Started | Medium | Food donation policy/process; donation partner agreement; donation logs; weight records; receipts from recipient organization. | Cal Zero Waste
55 | Reuse 7 | Participate in an animal feed program for inedible food. | Locate organizations within the area that need it for feeding animals and arrange for them to take the food. | As food waste is generated | As Needed | Not Started | Low | Animal feed partnership agreement; collection procedures; weight logs; receipts or records from receiving organization. | Cal Zero Waste
COMPOST
56 | Compost 1 | Collect compostables separately from other materials. | Identify areas where organics are generated and provide collection bins that are labeled for organics. | Once | Before Opening | In Progress | High | Photos of organics bins and signage; floor plans/locations; narrative describing collection system. | Facilities
57 | Compost 2 | Compost, digest, or reuse yard trimmings. | Create and implement a system for collecting then composting, digesting and/or mulching all green waste generated through landscaping activities. | Once | Before Opening | Not Started | Medium | Landscaping waste collection procedures; composting/mulching process documentation; photos; contractor agreement if applicable. | Facilities
58 | Compost 3 | Compost food scraps and/or soiled paper on-site. | Create and implement a system for composting food scraps and/or soiled paper on-site. | Once, compost as needed | As Needed | Not Started | Medium | On-site composting program description; operating procedures; photos of compost system; records of materials composted. | Cal Zero Waste
59 | Compost 4 | Compost food scraps and/or soiled paper off-site. | Create and implement a system for composting food scraps and/or soiled paper off-site. | Once | Before Opening | Not Started | Medium | Compost service agreement; hauling records; invoices; photos of collection infrastructure; narrative describing process. | Facilities
60 | Compost 5 | Utilize/ reuse compost or mulch onsite. | Identify areas where compost or mulch would be beneficial to site landscape, then purchase and apply it to these areas. | Once | One-Time Setup | Not Started | Low | Narrative describing compost/mulch use areas; purchase records; invoices; photos showing application onsite. | Building Manager
61 | Compost 6 | Implement other process technologies for organic materials. | Utilize a separate process technology for organic materials that is beneficial, non-harmful and/or generates clean energy. | As food waste is generated | As Needed | Not Started | Medium | Documentation of alternative organics technology (e.g., Mill, biodigester, vermicomposting, dehydration system); operating records; photos. | Cal Zero Waste
62 | Compost 7 | Use compost from site for on-site food production. | Create a process of utilizing compost generated from the food waste on-site to grow new food for company use. | As compost accumulates | One-Time Setup | Not Started | Low | Narrative describing food production process; compost use records; photos of growing areas; documentation linking compost generation to food production. | Cal Zero Waste
ZERO WASTE PURCHASING
63 | Purchasing 1 | Adopt an EPP guideline or policy. | Write, adopt, and implement an EPP guideline or policy that reduces waste or addresses zero waste products, packaging, or services. | Once | Before Opening | In Progress | Critical | Written EPP policy/guideline; narrative explaining implementation; purchasing reports or receipts (optional but helpful). | Cal Zero Waste
64 | Purchasing 2 | Include preference for durable goods in EPP policy or guideline. | Include a directive in the written EPP policy or guideline that durable goods are first preference for purchase over disposable items. | Once | Before Opening | In Progress | High | EPP policy containing durable goods preference language; narrative explaining implementation; optional purchasing records. | Cal Zero Waste
65 | Purchasing 3 | Give preference to sustainably produced paper and wood products. | Write, adopt, and implement a guideline or policy stating that certified sustainably produced paper and wood products are first preference for purchase. | Once | Before Opening | In Progress | High | EPP policy containing sustainably produced paper/wood preference; narrative; optional purchasing records. | Cal Zero Waste
66 | Purchasing 4 | Identify EPP items in purchasing catalogs. | Ensure environmentally preferred items are identified as such in purchasing catalogs and/or websites. | Once | Before Opening | In Progress | High | Catalog screenshots; website screenshots; purchasing system screenshots showing EPP designation/labelling. | Cal Zero Waste
67 | Purchasing 5 | Track purchase of EPP | Create system to track the purchase of environmentally preferred products and materials that address zero waste. | Once | Before Opening | In Progress | High | Tracking system/spreadsheet; EPP purchasing reports; procurement logs documenting environmentally preferred purchases. | Purchasing
68 | Purchasing 6 | Give preference to used, refurbished, and/or remanufactured goods. | Create a written policy or enact a standard practice that used, refurbished, and/or remanufactured goods are first preference for purchase over new items. | Once | Before Opening | In Progress | Medium | Written policy giving preference to used/refurbished/remanufactured goods; narrative; purchasing examples/receipts. | Cal Zero Waste
69 | Purchasing 7.1 | Any additional EPP Practices. | EPP policy or standard practice that reduces waste or addresses zero waste products, packaging or services not currently recognized in any category of the rating system. | Once | Before Opening | In Progress | Medium | Narrative describing additional EPP practice; policy language; implementation evidence. | Cal Zero Waste
70 | Purchasing 7.2 | Any additional EPP Practices. | EPP policy or standard practice that reduces waste or addresses zero waste products, packaging or services not currently recognized in any category of the rating system. | Once | Before Opening | In Progress | Medium | Narrative describing additional EPP practice; policy language; implementation evidence. | Cal Zero Waste
71 | Purchasing 7.3 | Any additional EPP Practices. | EPP policy or standard practice that reduces waste or addresses zero waste products, packaging or services not currently recognized in any category of the rating system. | Once | Before Opening | Not Started | Medium | Narrative describing additional EPP practice; policy language; implementation evidence. | Cal Zero Waste
CLOSED LOOP
72 | Closed Loop 1 | Increase post-consumer recycled materials and reduce the use of virgin paper for office paper. | Create a written policy or enact a standard practice that requires the use of minimum 30% post- consumer recycled content for office/copy paper. | Once | Before Opening | Done | Medium | Written policy; narrative; procurement records/invoices | Cal Zero Waste
73 | Closed Loop 2 | Promote use of post-consumer recycled materials and cut down the use of virgin paper for janatorial paper products. | Create a written policy or enact a standard practice that requires the use of minimum 20% post- consumer recycled content paper for all janitorial paper products (including but not limited to: toilet paper, paper towels and seat covers). | Once | Before Opening | Done | Medium | Written policy; narrative; procurement records/invoices | Cal Zero Waste
74 | Closed Loop 3 | Purchase compst from local source. | If purchasing compost, purchase from the facility that composts your material. If no materials generated at your facility are being composted, purchase compost from a local source. | N/A | N/A | Not Started | Low | Written policy; narrative; procurement records/invoices | Facilities
75 | Closed Loop 4 | Closing loop by ensuring materials remain in local markets and come back to site. | Implement a process where as much material as possible from the facility is taking advantage of local reuse, recycling, or upcycling options. Buy back or use products or materials made from your materials. | Case by case basis | As Needed | Not Started | Medium | Narrative; contracts/agreements; invoices/receipts showing materials return to site | Multiple
REDESIGN
76 | Redesign 1 | Right size containers and service levels. | Evaluate all containers to ensure appropriate size and schedules are in place. Implement a strategy for the periodic review of these containers and adjust container sizes and pick-up frequencies with service provider accordingly. | Quarterly review | Ongoing (Quarterly) | In Progress | Medium | Narrative; photos; calculations; service agreements/change orders | Facilities
77 | Redesign 2 | Ensure collection agreements are zero waste. | Review solid waste collection agreements for ALL vendors handling waste and reusable/recyclable materials. Identify and implement modifications to at least one agreement that incentivizes the reduction of waste to landfill, incineration (WTE) and the environment. | Once | Before Opening | Not Started | Medium | Narrative; contract amendments; written requests; updated agreements | Building Manager
78 | Redesign 3 | Review all points of generation. | Review all applicable points of generation for opportunities to ensure each material meets highest and best use in that area as compared to baseline practices. | Once | Before Opening | Not Started | High | Narrative; reports; meeting minutes; assessment documentation | Multiple
79 | Redesign 4 | Review supply chain. | Review purchasing records and supply chain agreements to determine opportunities to design out or eliminate wasting from vendors. Take at least one action that reduces waste from a vendor. | Once | As Needed | Not Started | High | Narrative; purchasing records; invoices; vendor communications; contract revisions | Building Manager
INNOVATION
80 | Innovation 1 | Pick from options. | Depends on selection of credit. | Once | As Needed | Not Started | Medium | Narrative; implementation documentation; supporting evidence | Cal Zero Waste
81 | Innovation 2 | Pick from options. | Depends on selection of credit. | Once | As Needed | Not Started | Medium | Narrative; implementation documentation; supporting evidence | Cal Zero Waste
82 | Innovation 3 | Pick from options. | Depends on selection of credit. | Once | As Needed | Not Started | Medium | Narrative; implementation documentation; supporting evidence | Cal Zero Waste

## 12-Month Follow-Up Calendar
12-Month Follow-Up Calendar - TRUE Operations Tracking
Track completion of recurring tasks. Mark each month: Done / Missed / Upcoming / N/A
# | Credit ID | Task | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027
LEADERSHIP
1 | Lead 2 | Monthly diversion review meeting | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
2 | Lead 3 | Employee recognition / suggestion review | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
TRAINING
3 | Train 3 | Quarterly zero waste communication | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
4 | Train 4 | Weekly bin labeling site walk | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
ZERO WASTE ANALYSIS
5 | ZWA 1 | Physical waste audit | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
6 | ZWA 2 | Analyze audit results + implement changes | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
7 | ZWA 3 | Physical audit of recyclables | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
8 | ZWA 4 | Update contamination data in diversion totals | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
9 | ZWA 5 | Employee engagement in audit/analysis | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
UPSTREAM MANAGEMENT
10 | Upstream 1 | Review vendor packaging compliance | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
REDUCE
10 | Reduce 1 | Identify at least 1 material the is being reduced/ track reduction | Upcoming | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Upcoming
10 | Reduce 2 | Establish regular reviews of data to identify wasteful activities. | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
REUSE
10 | Reuse 2 | Track and document the reuse of pallets, incoming and outgoing shipping containers monthly by weight. | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
10 | Reuse 6 | Determine where food fit for human consumption could be preserved and donated. | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
10 | Reuse 7 | Locate organizations within the area that need it for feeding animals and arrange for them to take the food. | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
COMPOST
10 | Compost 3 | Compost food scraps and/or soiled paper on-site. | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
10 | Compost 6 | Utilize a separate process technology for organic materials. | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
REDESIGN
10 | Redesign 1 | Review and adjust container sizes and pick-up frequencies with service provider accordingly. | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
ZERO WASTE REPORTING
| Zero Waste Reporting 1&2 | Enter monthly diversion & financial data by commodity and waste stream | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
| Zero Waste Reporting 3 | Update EPA WARM model inputs | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Upcoming
| Zero Waste Reporting 4 | Update WasteWise reporting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Upcoming
RECYCLE
| Recycle 1.1&1.2 | Review highest-and-best-use status for major material streams | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
| Recycle 2 | Follow up with haulers/service providers on end-market documentation | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
DIVERSION FROM LANDFILL, INCINERATION (WTE), AND ENVIRONMENT
| Diversion 1.1–1.5 | Calculate monthly diversion rate and check if ≥90% | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
| Diversion 1.1–1.5 | Flag any contamination or landfill spikes for corrective action | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming | Upcoming
HAZARDOUS WASTE PREVENTION
| HWP 2 | Save records and update documentation folder for hazardous waste manifests and records | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming
| HWP 3&5 | Track e-waste, batteries, bulbs, and other universal waste collection | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming | N/A | N/A | Upcoming

## Pre-Opening Checklist
Pre-Opening Checklist - Must Complete Before TCO / Building Opens
These items must be in place BEFORE operations begin (Target: June 2026). Complete these first!
| Credit | Task | Specific Steps | Target Date | Status | Owner | Notes
POLICIES & GOALS
| Lead 1 | Adopt/post zero waste goal | 1. Draft operations ZW goal document 2. Get upper management sign-off 3. Post in building lobby + common areas 4. Include in building welcome packet | May 2026 | In Progress | Building Manager | "Divert 90%+ of waste from the landfill" within our policy and slides.
| Train 1 | Distribute ZW policy to all occupants | 1. Include ZW policy in department handbooks 2. Post near all bin stations 3. Email to all building occupants before move-in 4. Add to building website | May 2026 | Not Started | Building Manager | Our manual
| Train 7 | Appoint Zero Waste Champion | 1. Identify person with ZW in job description 2. Formalize appointment 3. Communicate role to building community | May 2026 | In Progress | Building Manager | "responsible for Zero Waste training and Program management" Sam?
| Train 9 | Ensure TRUE Advisor on team | 1. Verify current TRUE Advisor credentials 2. Train new team members if needed 3. Upload certificates | May 2026 | In Progress | UCB Team | Audrey
| ZWP 1 | EPP Policy | 1. Draft EPP policy. 2. Define approved product attributes. 3. Define purchasing hierarchy. 4. Obtain management approval. 5. Publish policy. | 2026-06-01 | In Progress | Cal Zero Waste | Manual
| ZWP 2 | Preference for durable goods. | 1. Add durable-first language to EPP. 2. Identify common disposable products. 3. Replace with durable alternatives. | 2026-06-01 | In Progress | Cal Zero Waste | Manual
| ZWP 3 | Require sustainable paper and wood. | 1. Define acceptable certifications. 2. Add requirements to purchasing guidance. 3. Update procurement documents. | 2026-06-01 | In Progress | Building Manager | Manual
| ZWP 6 | Preference for refurbished and remanufactured goods. | 1. Add requirement to EPP. 2. Establish review process. 3. Create documentation procedure. | 2026-06-01 | In Progress | Cal Zero Waste | Manual
| Closed Loop 1 | Require a minimum 30% PCR office paper. | 1. Add language to EPP. 2. Identify approved products. 3. Communicate requirement to purchasers. | 2026-06-01 | In Progress | Building Manager | Manual, but how can we implement?
| Closed Loop 2 | Require a minimum 20% PCR janitorial paper. | 1. Add requirement to custodial purchasing standards. 2. Verify approved products. 3. Update supplier lists. | 2026-06-01 | In Progress | Building Manager | Discuss with Sandra Vargas (Custodial Assistant Manager, sandra.enamorado@berkeley.edu) and Rocio Rodriguez (Supervisor, rocrg-1@berkeley.edu), policy in manual
| Hazardous Waste Prevention 1 | Confirm hazardous material storage/labeling policy and training process | 1. Confirm applicable hazardous materials for building operations. 2. Locate existing UC/campus hazardous material policy. 3. Confirm storage areas, labels, SDS access, and disposal process. Cofim disposal practices comply with HAZCOM, RCRA, and applicable federal, state, and local requirements. 4. Identify training owner and upload training/policy documents. | 2026-06-01 | In Progress | Building Manager | Not sure what hazardous material will be in this building, but we can also connect with EH&S after discussing with Sarah
| Hazardous Waste Prevention 3 | Identify universal waste streams & disposal strategies: batteries, e-waste, bulbs, toner, etc. | 1. List expected universal waste streams: e-waste, batteries, lamps/bulbs, toner, and small electronics. 2. Confirm collection locations and responsible department. 3. Confirm approved disposal/recycling vendor. 4. Save service documentation or campus procedure. | 2026-06-01 | In Progress | Building Manager | Let's put battery collection tubs in the ReUse stations! Other hazardous waste goes through this process.
| Hazardous Waste Prevention 4 | Locate all hazardous materials to be used in the building and create a policy for reducing hazardous chemicals/materials | 1. Inventory chemicals/materials expected in custodial, maintenance, labs, kitchens, and building operations. 2. Identify safer or less hazardous alternatives. 3. Add reduction expectations to purchasing/EPP or custodial standards. 4. Save policy language and implementation evidence. | 2026-06-01 | In Progress | Purchasing | Discuss with Sandra Vargas (Custodial Assistant Manager, sandra.enamorado@berkeley.edu) and Rocio Rodriguez (Supervisor, rocrg-1@berkeley.edu). Also, I'm writing a grant right now to get a Tersano in this building, so this will reduce hazardous cleaning chemicals
| Hazardous Waste Prevention 5 | Decide whether employee/customer universal waste collection will be offered | 1. Decide whether occupants can drop off batteries, e-waste, toner, or other universal wastes. 2. Define accepted items, location, and collection frequency. 3. Assign monitoring and pickup owner. 4. Create occupant-facing instructions/signage. | 2026-06-01 | In Progress | Building Manager | check with sarah
TRAINING & ORIENTATION
| Train 2 | Build ZW into orientation | 1. Create orientation slides with ZW content 2. Include bin map + sorting guide 3. Add contamination examples 4. Incentivize occupants before building access | May 2026 | In Progress | Building Manager | Sam has bin map, Andrea made slides for this. When can we schedule these sessions?
| Train 4 | Label ALL bins + prepare training | 1. Install clear labels on every bin (recycling, compost, landfill) 2. Use multilingual signage 3. Prepare sorting guide handout 4. Schedule weekly walk-through plan | May 2026 | In Progress | Building Manager | Our bins do not have multilingual signage, but I wonder if we can still get the credit if I put multiple languages on our website, where the QR code goes
| Train 5 | Train purchasing agents | 1. Identify all people who make purchases 2. Create/update EPP training materials 3. Schedule initial training session 4. Distribute EPP catalog/guidelines | Jun 2026 | Not Started | Purchasing | Need these contacts, for getting their gauge on most used products too so that we can get a quote from Blaisdells about discounts.
| Train 8 | Set up online ZW training access | 1. Create or link ZW training on building website 2. Include sorting guides, FAQ, resources 3. Ensure all occupants can access | Jun 2026 | Not Started | Cal Zero Waste | Can we incorporate Andrea's training slides on here, accessible for everyone?
| Reuse 1 | Create building-wide reuse systems. | 1. Establish reuse systems like Dispatch, dishware, Circularity Kit, and ReUse stations.. 2. Create redistribution procedures. 3. Communicate to occupants. | 2026-06-01 | In Progress | Cal Zero Waste
| Reuse 4 | Office Supply reuse program, create collection and redistribution processes. | 1. Designate collection area. (ReUse stations) 2. Establish management process. 3. Develop communication materials. | 2026-06-01 | In Progress | Cal Zero Waste
| Reuse 5 | Replace disposable kitchen products. | 1. Determine inventory for kitchens. 2. Purchase durable products. 3. Establish washing procedures. 4. Remove disposable alternatives. | 2026-06-01 | In Progress | Cal Zero Waste
| Compost 1 | Create a compost collection system and train occupants. | 1. Install bins. 2. Install signage. 3. Define accepted materials. 4. Train occupants. | 2026-06-01 | In Progress | Building Manager
| Reduce 4 | Convert one major process to digital. | 1. Identify process. 2. Implement digital workflow. 3. Estimate paper reduction. | 2026-06-01 | Not Started | Building Manager | When we do the training with occupants, perhaps we ask them their ideas for what process we could target, unless Sarah/Domenico have an idea already
| Reduce 5 | Set printers to default duplex. | 1. Inventory printers. 2. Update settings. 3. Communicate policy. | 2026-06-01 | In Progress | Building Manager | policy in manual but need to be more clear.
| Hazardous Waste Prevention 1 | Confirm hazardous material storage/labeling policy and training process | 1. Confirm hazardous materials expected during operations. 2. Verify storage, labeling, SDS, and disposal procedures. 3. Confirm training requirements. 4. Save policy/training and optional photos. | 2026-06-01 | In Progress | Building Manager | Batteries, anything else? Check with Sarah if there's any other hazardous waste (esp labs)
VENDOR & UPSTREAM SETUP
| Lead 5 | Vendor take-back contracts | 1. Review all vendor contracts for take-back language 2. Negotiate at least one vendor agreement 3. Document reusable packaging arrangements | May 2026 | Not Started | Purchasing | regular vendors we can do this with? have any vendor contracts been made yet or are planning to be made?
| Upstream 1 | Vendor packaging reduction requests | 1. Identify top 5 vendors by packaging volume 2. Send formal request for reduced/reusable packaging 3. Document all requests and responses | Jun 2026 | Not Started | Purchasing | who? Blaisdells?
| Upstream 3 | Request 100% recyclable packaging | 1. Draft standard request letter 2. Send to all key vendors 3. Track responses | Jun 2026 | Not Started | Purchasing
| Reuse 3 | Replace disposable shipping containers where feasible. | 1. Identify supply deliveries. 2. Identify reusable tote opportunities. 3. Engage vendors. 4. Pilot reusable container system. | 2026-06-01 | Not Started | Building Manager | Check with Lin on current shipping crate policy. I think vendors must take them back
| Compost 2 | Ensure all landscape waste is composted, mulched, or reused. | 1. Review landscaping contract. 2. Add diversion requirement for landscape waste. 3. Identify processor. 4. Establish verification process for documentation. | 2026-06-01 | Not Started | Facilities | Discuss with Lydia Woltjer (Landscape manager, lwoltjer@berkeley.edu)
| Compost 4 | Establish compost hauling service for off-site composting. | 1. Select compost processor. 2. Confirm accepted materials. 3. Execute service agreement. 4. Train custodial and occupants. | 2026-06-01 | In Progress | Facilities | This is done
| Compost 5 | Use compost or mulch on-site. | 1. Identify landscape locations. 2. Determine annual need. 3. Coordinate with grounds staff. | 2026-06-01 | Not Started | Facilities | Discuss with Lydia Woltjer (Landscape manager, lwoltjer@berkeley.edu). Other possibility could be community garden on Gateway rooftop?
| Reduce 6 | Leave grass clippings on lawns. | 1. Review landscaping contract. 2. Add grasscycling requirement. 3. Verify implementation. | 2026-06-01 | Not Started | Facilities | Discuss with Lydia Woltjer (Landscape manager, lwoltjer@berkeley.edu)
| Reduce 7 | Reduce trimming waste through landscape design. | 1. Review planting plan. 2. Identify low-maintenance species. 3. Establish long-term replacement strategy. | 2026-06-01 | Not Started | Building Manager | Discuss with Lydia Woltjer (Landscape manager, lwoltjer@berkeley.edu)
| ZWP 4 | Make preferred products easy to find. | 1. Work with suppliers. 2. Label EPP items. 3. Build approved product lists. | 2026-06-01 | In Progress | Cal Zero Waste | Bearbuy- Alex is doing this once we send him what to mark with it. Blaisdells already does this.
| ZWP 7.1-3 | Preference for products with (ex. minimal packaging, reusable, refillable systems). | 1. Implement policy. | 2026-06-01 | Not Started | Cal Zero Waste
| Redesign 1 | Right-Size collection containers. | 1. Review all collection points. 2. Estimate generation volumes. 3. Determine proper bin sizes. 4. Determine service frequencies. | 2026-06-01 | Not Started | Building Manager | Sarah and I will be doing this.
| Redesign 2 | Align hauling contracts with zero waste goals and incentivize diversion. | 1. Review hauling agreements. 2. Add diversion incentives. 3. Add contamination expectations. 4. Add reporting requirements. | 2026-06-01 | Not Started | Building Manager | This is done since it's internal UCB haulers and we all have the UCB Sustainability policy; but we can get details on contamination expectations from Kevin Taplin
| Redesign 4 | Supply chain review, and identify waste generation from vendors. | 1. Review major suppliers. 2. Identify unnecessary packaging. 3. Engage vendors. 4. Document improvement actions. | 2026-06-01 | Not Started | Cal Zero Waste | Waxie is one of our biggest suppliers so it would be great to review their packaging. I feel like we should focus in on soap dispensers since I'm assuming we buy liquid soap instead of concentrate. I think UCSC just did something about this a year ago
| Recycle 1.1 / 1.2 | List applicable material categories and determine highest-and-best-use pathway for each | 1. List applicable material categories. 2. Match each stream to highest-and-best-use pathway. 3. Identify any gaps. 4. Build calculation template by weight. | 2026-06-01 | Not Started | Cal Zero Waste
| Recycle 2 | Identify all recycling/compost/service providers and request end-market letters | 1. List all recycling, compost, and hauling service providers. 2. Confirm provider locations. 3. Request written end-market documentation. 4. Save letters/emails in documentation folder. | 2026-06-01 | Not Started | Cal Zero Waste | Ask Danner first if she already has these? Then ask KEvin
DATA SYSTEMS & BASELINE
| ZWA 1-3 | Set up waste audit schedule | 1. Schedule first physical waste audit for Month 1 2. Create audit checklist/template 3. Assign audit team 4. Set quarterly recurring calendar reminders | Jun 2026 | Not Started | Building Manager | Sam will help coordinate; just need to know what month to target since occupants are moving in in a rolling basis
| ZWA 4 | Set up contamination tracking system | 1. Coordinate with hauler on contamination reporting 2. Create tracking spreadsheet 3. Define methodology for adding contamination to non-diversion totals | Jun 2026 | Not Started | Building Manager | Ask Danner for her sheet
| Lead 2 | Set up monthly review meeting cadence | 1. Schedule recurring monthly meeting 2. Create agenda template (diversion data, financials, action items) 3. Invite leadership + ZW team | Jun 2026 | In Progress | Building Manager
| ZWP 5 | Create a purchasing tracking system. | 1. Define tracked products. 2. Build spreadsheet/database. 3. Create reporting process. 4. Assign ownership. | 2026-06-01 | In Progress | Cal Zero Waste | Can we receive list of purchases that are delivered to Gaetway from BearBuy? Ask Alex
| Redesign 3 | Review all points of generation, and map all waste generation locations. | 1. Identify applicable generation areas: Offices, Social Kitchens, Housing/Events, Grounds, Receiving & Loading Dock 2. Document waste streams generated in each area. 3. Determine highest and best use. 4. Identify infrastructure needs. 5. Identify improvement opportunities. | 2026-06-01 | Not Started | Cal Zero Waste
| Zero Waste Reporting 1 & 2 | Confirm methodology for monthly waste tracking (diversion data + financial tracking) | 1. Create monthly waste tracking spreadsheet by commodity and waste stream. 2. Create financial tracking columns for disposal costs, diversion costs, avoided costs, and revenue. 3. Confirm baseline year and reporting year. 4. Define actual-weight vs. estimated-weight methodology. | 2026-06-01 | Not Started | Cal Zero Waste | get tracking sheet from Danner
| Zero Waste Reporting 3 | Download/set up EPA WARM model | 1. Download the EPA WARM model. 2. Map Gateway waste streams to WARM material categories. 3. Save generated report & familiarize with data needed. | 2026-06-01 | Not Started | Cal Zero Waste
| Zero Waste Reporting 4 | Confirm Gateway's participation in EPA WasteWise | 1. Confirm whether UC Berkeley/Gateway will enroll or report through EPA WasteWise. 2. Identify account owner. 3. Save membership confirmation. 4. Add annual reporting reminder. | 2026-06-01 | Not Started | Cal Zero Waste
| Diversion 1.1–1.5 | Decide how monthly diversion data will be tracked and collected | 1. Build monthly diversion calculation template. 2. Confirm data source for each stream. 3. Review monthly progress toward 90%+ diversion. | 2026-06-01 | Not Started | Cal Zero Waste | We will prob just get the weekly reporting sheets from Cal Zero Waste and use Danner's excel sheet to calculate diversion on a monthly basis

## Legend & Instructions
How to Use This Tool
STATUS COLORS
| Not Started | Task has not been started yet
| In Progress | Task is underway but not complete
| Done | Task is fully complete with evidence collected
| N/A | Not applicable to this project
PRIORITY LEVELS
| Critical | Must be completed - required for certification
| High | Strongly recommended - significant point value
| Medium | Recommended - contributes to certification score
| Low | Optional - pursue if time/resources allow
PHASE GUIDE
| Before Opening | Must be in place BEFORE the building opens (before TCO)
| At Opening | Set up during the first month of operations
| Ongoing (Monthly) | Recurring task - do every month
| Ongoing (Quarterly) | Recurring task - do every quarter
| Ongoing (Annually) | Recurring task - do every year
| One-Time Setup | Do once and maintain
12-MONTH CALENDAR
| Done | Task was completed this month
| Missed | Task was due but NOT completed
| Upcoming | Task is scheduled for this month
| N/A | Task is not due this month
SHEETS OVERVIEW
| Credit Tracker | Master list of ALL credits with requirements, status, and evidence needs
| 12-Month Calendar | Track recurring tasks month-by-month for the first year of operations
| Pre-Opening Checklist | Tasks that MUST be done before the building opens (June 2026)